## Sheet1
		Weekly goalplan master
	Week	Goal 1	Goal 2	Goal 3	Goals reached	Goals pushed
January	2	Make weekplan	Continue Litterature Review
	3	Old Model in AMPL	Start final Model	Ask for instances/clear Questions
	4	Finish final model	Start AMPL final Model	Get instances
February	5	Start Java Program	Finalize AMPL final model
	6	Cont Java program
	7	Cont Java program
	8	Cont Java program
March	9	Finalize java Program
	10	Finalize java Program
	11	Finish Java Program
	12	Analyze Results
	13	Analyze Results
April	14	Analyze Results
	15	Finish analysis and Results
	16	Easter Holiday
	17	Easter Holiday
Mai	18	Write out results
	19	Write out results
	20
	21
Juni	22
	23
	24
	25
	26
Juli	27
	28
	29
	30
August	31
	32
	33
	34
September	35
	36
	37
	38
	39
Oktober	40	DEADLINE
	41
	42